**Event Planning Checklist**

|  |  |  |  |
| --- | --- | --- | --- |
| **Event Planning Assignments** | **Timeline** | **Person/s Responsible** | **Task** **Completed** |
| Confirm event date and time | 3-6 months |  |  |
| Develop a budget | 3-6 months |  |  |
| Reserve event location  | 3-6 months |  |  |
| Contact potential sponsors if needed | 3-6 months |  |  |
| Identify target audiences to promote the event  | 3-6 months |  |  |
| Contact/Confirm speaker if neededNote: A PowerPoint presentation is available at www.nationalhealthcaredecisionsday.org (under “educate your community”) | 3-6 months |  |  |
| Copy/Print flyer/poster - template available at www.nationalhealthcaredecisionsday.org (under “educate your community”) | 2-4 months |  |  |
| Post event in newsletters and/or on Website | 2-4 months |  |  |
| Develop marketing plan | 2-4 months |  |  |
| Recruit volunteers to assist with marketing and assist with event  | 2-4 months |  |  |
| Draft program agenda | 2-3 months |  |  |
| Contact refreshment venues | 2 months |  |  |
| Distribute event flyers/posters/mailing | 2 months |  |  |
| Develop PR or press kit from materials available atwww.nationalhealthcaredecisionsday.org (under “educate your community”) | 2 months |  |  |
| Rent chairs, tables, projector or other equipment if need  | 2 months |  |  |
| Find state approved advance directive to distribute at event | 1-2 months |  |  |
| Finalize presentation if needed -Edit PowerPoint presentation to contain your organization’s information and local resources | 1-2 months |  |  |
| Hold an information session before the event to educate those working the event if needed | 1 months |  |  |
| Arrange media interview with local expert – newspaper, radio and/or TV | 3-4 weeks |  |  |
| Draft room layout | 2-3 weeks |  |  |
| Finalize volunteer schedule & tasks for event | 2-3 weeks |  |  |
| Review AV needs and confirm reservations | 2-3 weeks |  |  |
| Print final program | 1 week |  |  |
| Print handouts | 1 week |  |  |
| Print participant sign-in forms and feedback forms located in Toolkit | 1 week |  |  |
| Finalize and confirm refreshments | 1 week |  |  |
| Print badges if need | 1 week |  |  |
| Make signs to direct attendees to event location/room | 1 day |  |  |
| Set up event location, registration area, put up signs, etc. | 1 day |  |  |
| [Add more items if need to this checklist] |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
| **After event:**Summarize participant feedback forms and media coverage |  |  |  |
| Complete NHDD evaluation |  |  |  |
| [Add more items as needed to this checklist] |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |